| Date | 07 July 2026 |
| --- | --- |
| Team ID | NA |
| Project Name | HouseHunt (MERN House Rental Platform) |
| Phase | Project Planning Phase |

Project Planning Document

1. Project WBS Plan & Milestones

| WBS Code | Phase / Task Name | Assigned Role | Estimated Duration | Milestone Deliverable |
| --- | --- | --- | --- | --- |
| 1.0 | Requirements & Design Phase | System Architect & UI Designer | 5 Days | Functional Specifications & UI Prototypes |
| 1.1 | Compile layout specifications & assets specs | Hemasundararao Meesala | 1 Day | Style guide sheet completed |
| 1.2 | Map database Mongoose schemas | Hemasundararao Meesala | 2 Days | Database schema draft compiled |
| 1.3 | Design UI wireframes & page routing structures | Dona Sri Divya Nerusu | 2 Days | UI wireframe diagrams signed off |
| 2.0 | Backend Core Development | Senior Backend Developer | 10 Days | Complete running backend REST API |
| 2.1 | Initialize Express.js app & router configurations | Harshitha Nulu | 2 Days | Repository structure pushed |
| 2.2 | Establish MongoDB Mongoose connection | Rajani Meesala | 1 Day | DB link confirmed |
| 2.3 | Implement authentication, password hashing, and OTP | Harshitha Nulu | 4 Days | Signup & login flows working |
| 2.4 | Configure Multer file uploading middlewares | Varshitha Nagadasi | 3 Days | Avatar and house multi-uploads completed |
| 3.0 | Frontend Client Development | Senior Frontend Developer | 10 Days | Interactive responsive React client |
| 3.1 | Bootstrap Vite React project structure | Varshitha Nagadasi | 1 Day | Vite React app initialized |
| 3.2 | Configure global themes variable (Sun & Moon) | Hemasundararao Meesala | 2 Days | index.css theme styles complete |
| 3.3 | Code public auth pages (Login, Register, OTP) | Rajani Meesala | 4 Days | Signup/login templates validated |
| 3.4 | Build search filter bar & listings cards feed | Dona Sri Divya Nerusu | 3 Days | Browse page UI completed |
| 4.0 | Role Progression & Moderation | MERN Developer | 8 Days | End-to-end Tenant-to-Owner workflow |
| 4.1 | Write property submit router (Pending status) | Harshitha Nulu | 2 Days | Submissions POST route tested |
| 4.2 | Code Admin approval controller & upgrade user role | Rajani Meesala | 2 Days | Tenant-to-Owner role upgrade complete |
| 4.3 | Build renter submission tab & landlord hub tables | Dona Sri Divya Nerusu | 4 Days | Dashboards UI integrated |
| 5.0 | Verification & Final Launch | QA Engineer & Lead Developer | 5 Days | Fully tested production-ready package |
| 5.1 | Perform API endpoints tests & database checks | Varshitha Nagadasi | 2 Days | API testing logs compiled |
| 5.2 | Compile production build (Vite build) | Hemasundararao Meesala | 1 Day | Static assets folder compiled |
| 5.3 | Generate complete documentation guide | Hemasundararao Meesala | 2 Days | DOCUMENTATION.md generated |

2. Risk Management Plan Matrix

| Risk ID | Risk Description | Severity (1-5) | Probability | Mitigation Strategy | Contingency Action Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | Windows filesystem locking temporary Vite dependency cache directories (EPERM error). | 2 (Low) | Medium | Configure npm run dev to automatically delete .vite folder in node_modules prior to calling vite. | Hemasundararao Meesala (Lead Developer) |
| R2 | Local MongoDB server connection failure during launch. | 5 (Critical) | Low | Ensure backend connects to local port 27017 with robust catch logs. Pre-program mock database objects inside dashboards as a fallback. | Rajani Meesala (DB Architect) |
| R3 | Google Mail SMTP authentication credentials blocked or missing in production. | 4 (High) | Medium | Program an automatic Terminal email simulator fallback. If credentials are empty, OTP code prints to console for verification testing. | Harshitha Nulu (Security Engineer) |
| R4 | Self-booking loop where landlord books their own property, locking active leases. | 3 (Medium) | Low | Implement validation checks in the backend controller matching property.ownerId with req.user.id and block with 400 Bad Request. | Dona Sri Divya Nerusu (Team Lead) |
| R5 | Performance degradation due to unoptimized property image loading size. | 3 (Medium) | Medium | Constrain Multer files upload to standard size limits (max 5MB per file) and compress/optimize image rendering grids in React. | Varshitha Nagadasi (Frontend Member) |